## Worksheet
PCBA Board Details
Product Name | Laptop
Product Model
Bom Name | Bom1
Bom Revision | 1
BOM Description | 1
Number of unique components (Considered for analysis) | 14
BU | Dell site1
Division | Dell div1
Supplier Name
EAU
Risk Calculated Date | 27-Dec-2022
Date of Actual Scrub | 27-Dec-2022
Board Level Risk | HiRisk
Immediate Risk Summary
Description | Internal IPNs
Total Risks | 11
High Risk | 9
Med Risk | 0
Low Risk | 2
No Risk | 3
Active Parts
Description | ROHS3 | EOL | LTB | NRND | NRND,REACH | REACH | REACH,Supply Lead Time | Supply Lead Time | Unconfirmed
High Risk | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Med Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Low Risk | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Total Risks | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
Passive Parts
Description | ROHS3 | EOL | LTB | NRND | NRND,REACH | REACH | REACH,Supply Lead Time | Supply Lead Time | Unconfirmed
High Risk | 3 | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 0
Med Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Low Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Risks | 3 | 1 | 1 | 0 | 0 | 0 | 1 | 2 | 0
Internal Part number | IPN Description | Manufacturer Name | Manufacturer Part Number | Active / Passive | Risk Priority | Type of Risk @ IPN | ECR/EPD Number | Project Status | Proje=ct Owner | Start Date | Target Date | Completion Date | Design/Supply Risk | Immediate Owner | Supplier Info Received Date | Cover date based on Supplier input @IPN level | Cover date based market availability @IPN level
B110001 | CONN DC/DC 3A 24VIN POS SMD | Murata | 110001 | Passive | HiRisk | LTB | NA | NA | NA | NA | NA | NA | design_risk | NA | 2022-12-27 00:00:00 | 2024-10-21 00:00:00 | 2024-10-01 00:00:00
B110002 | CERAMIC RES 10.0000MHZ 33PF SMD | Murata | 110002 | Passive | HiRisk | REACH,Supply Lead Time | NA | NA | NA | NA | NA | NA | sourcing_risk | NA | 2022-12-27 00:00:00 | 2022-10-03 00:00:00 | 2023-02-06 00:00:00
B110003 | CAP FILM 2.2UF 400VDC RADIAL | Panasonic | 110003 | Passive | HiRisk | Supply Lead Time | NA | NA | NA | NA | NA | NA | sourcing_risk | NA | 2022-12-27 00:00:00 | 2022-03-24 00:00:00 | 2023-02-09 00:00:00
B110004 | CAP CER 4.7UF 25V 10% X7R 0805 | Taiyo Yuden | 110004 | Passive | HiRisk | ROHS3 | NA | NA | NA | NA | NA | NA | design_risk | NA | 2022-12-27 00:00:00 | 2022-05-04 00:00:00 | 2032-12-24 00:00:00
B110005 | INDUCTOR POWER 6.8UH 550MA SMD | Taiyo Yuden | 110005 | Passive | NoRisk | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2022-12-27 00:00:00 | 2023-09-10 00:00:00 | 2028-10-20 00:00:00
B110006 | CONN HEADER 2POS .100" SNGL GOLD | Samtec | 110006 | Passive | NoRisk | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2024-07-23 00:00:00
B110007 | CONN HEADER 6POS .100" SNGL GOLD | Samtec | 110007 | Passive | NoRisk | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2026-05-25 00:00:00
B110008 | OPTOISOLATR 5KV TRANSISTOR 4-SMD | Lite-On | 110008 | Active | LowRisk | Supply Lead Time | NA | NA | NA | NA | NA | NA | sourcing_risk | NA | 2022-12-27 00:00:00 | 2024-10-21 00:00:00 | 2026-08-29 00:00:00
B110009 | CRYSTAL 6.0000MHZ 18PF SMD | Abracon LLC | 110009 | Active | HiRisk | ROHS3 | NA | NA | NA | NA | NA | NA | design_risk | NA | 2022-12-27 00:00:00 | 2023-10-27 00:00:00 | 2023-11-21 00:00:00
B110010 | CAP FILM 0.1UF 20% 305V MKP X2 | Samsung | 110010 | Passive | HiRisk | EOL | NA | NA | NA | NA | NA | NA | design_risk | NA | 2022-12-27 00:00:00 | 2023-10-27 00:00:00 | 2026-03-09 00:00:00
B110011 | CAP ALUM 330UF 35V 20% RADIAL | AVX Corporation | 110011 | Passive | HiRisk | Supply Lead Time | NA | NA | NA | NA | NA | NA | sourcing_risk | NA | 2022-12-27 00:00:00 | 2022-12-10 00:00:00 | 2023-08-04 00:00:00
B110012 | CAP CER 2200PF 50V 10% X7R 0805 | Lite-On | 110012 | Passive | HiRisk | ROHS3 | p123 | CR - Plan | Dell coe | 2022-12-25 00:00:00 | 2022-12-31 00:00:00 | NA | design_risk | NA | 2022-12-27 00:00:00 | 2024-01-25 00:00:00 | 2032-12-24 00:00:00
B110013 | CAP CER 10UF 50V X5R 1206 | Samtec | 110013 | Passive | HiRisk | ROHS3 | p123 | CR - Plan | Dell coe | 2022-12-25 00:00:00 | 2022-12-31 00:00:00 | NA | design_risk | NA | 2022-12-27 00:00:00 | 2028-04-03 00:00:00 | 2032-12-24 00:00:00
B110014 | IC SGL SCHMITT BUFFER SOT353 | Taiyo Yuden | 110014 | Active | LowRisk | REACH,Supply Lead Time | NA | NA | NA | NA | NA | NA | sourcing_risk | NA | 2022-12-27 00:00:00 | 2024-10-21 00:00:00 | 2024-08-02 00:00:00